## A00 Baseboard #1
Jetbot Mini A00 Baseboard Bring Up Check Items |  | Location/Ref Des | Measured | Expected | Pass or Fail | Comments |  | PASS
Visual and Mechanical Inspection | [7 empty] | WIP
| Visually check all SMT components for tombstoning | - |  | - | PASS |  |  | FAIL
| Visually check for solder bridges | - |  | - | PASS | Note that R52 is deliberately solder bridged, as otherwise the button is not connected to the rest of the circuit
| Check silkscreen | J13, J9, SW1, J14, J1, R52, D10, C59, J8, J7, J5, J6, J12, J2, J3 |  | - | WIP | Check R52, D10 and C59 as they were meant to be NS options and user should be able to find them easily. Other checks are connectors, I/O and other important notes. Make sure things look clean, no weird logos, make sure things are aligned and neat, no smudges. Note that D10 silkscreen is misaligned and clips into the pads of C59. C30 is marked with silkscreen for some reason? D7 silkscreen is covered by capacitor. R19 silkscreen is clipped by the resistor pads. Battery GND + is very confusing, rework (J12). D5 is marked for no reason. Barrel Jack Text is slightly clipped by U3 and C40. Need to add silkscreen for UART (J14), OLED (J13), Fan (J9).
| Check U18, F1, J5 (DC Jack), C11, C46, D5, D8, L2, L3 | U18, F1, J5, C11, C46, D5, D8, L2, L3 |  |  | PASS | These footprints were made by me, so make sure that all the parts look soldered on correctly C11 and C46 look a little small for the components, can't see any of the pads underneath. Double check these component?
| Module fitting in SODIMM connector | J1 |  | - | PASS
Short circuit Check
| Check for short on Barrel_Jack_Vin | J5 |  | - | PASS
| Check for short on Battery_PWR | J12 |  | - | PASS
| Check for short on Charger_Output | C19 |  | - | PASS
| Check for short on +5V_AO | U15 pin 1 |  | - | PASS
| Check for short on +5V | L3 or J14 |  | - | PASS
| Check for short on +3.3V | L1 |  | - | PASS
| Check for short on +1.8V | U24 pin 5 |  | - | PASS
| Check for short on microUSB VBUS, D+, D- nets | J7 |  | - | PASS | microUSB not working, so need to troubleshoot why
| Check for short on Camera Nets |  |  | - | PASS
Voltage and Current Check
| Charging Current | R38 | 1.4 A | 1.5 A | WIP | Use the current sense resistor R38, measure voltage across it and check V = iR for the current. Double check why the current value is off. | C denotes maximum charge rate, every battery has a specific maximum charge current, and worst case you can damage or destroy it.
| Long Charge |  |  |  |  | Make sure when long charging, the voltage of the battery is properly regulated.
| Charger_Output | C19 | 12.16 V | See Comments | PASS | If barrel jack plugged in, should be barrel jack voltage, and if battery plugged in, should be at battery voltage, if both plugged in then should be barrel jack voltage
| 5V_AO | U15 pin 1 | 5.05 V | 4.75 - 5.25 V | PASS
| 5V | L3 | 5.20 V | 5 V | WIP | After pressing button turns on. Initial state is off when power is plugged in? Voltage is a little higher than expected, perhaps because of incorrect values, also double check calculations. After plugging in Jetson Nano module, more like 5.10 V? | 12 V: 5.20 15 V: 5.20 19 V: 5.20
| 3.3V | L1 | 3.248 V | 3.3 V | WIP | 3.3 V enable signal @3.387 V even though module is not plugged in???? Because the pin is floating, should go low once the module is plugged in, double check the pullups on all the datasheets.
| 1.8V | U24 pin 5 | 1.801 V | 1.8 V | PASS
Functional Check
| 10s button press shutdown | Short R52 and hold PWR_BTN |  |  | PASS | Once the module is powered on, should turn off the module.
| Button Power On | Press PWR_BTN after shutting off the module with 10s press down |  |  | PASS | Initial state is off when power is plugged in????? However when you press button, 5V turns on as expected
| Software Shutdown Req | After powering on the module, shutdown with software |  |  | FAIL | Cannot shutdown from software, had to remove buffer as it was pulling RESET low always, which never turns on the 5V buck converter, which never powers on the module.
| UART | Power on with barrel jack, Connect FTDI friend to baseboard and host computer |  |  | PASS | Check if you can create a serial connection with Putty and login to the Jetson Nano. Was able to do this after making modification to 3V3 buck converter enable signal. Does 5V need to be connected? Note that PWR_LED will turn on even if just UART is connected Switch Rx and Tx on A01 to make compatible with FTDI dongle
| Force Recovery from UART (check microUSB) | Power on with barrel jack or battery, connect FTDI friend to baseboard |  |  | PASS | Onced powered on, use Putty to create a serial connection, stop booting and type in "enterrcm", and check for device in Windows Device manager Works at both 12 V and 19V?
| Check PWR_LED | D6 |  |  | PASS | Turns off and on as expected
| Get Wifi Dongle Working |  |  |  | PASS | Download drivers, establish a wifi connection, try to log in via ssh.
| Check ACOK | D3 |  |  | PASS
| Check CHGOK | D4 |  |  | PASS
| Check USB 2.0 Type A | J8 |  |  | PASS | Connect mouse or keyboard, or connect a USB drive and see if it appears. Make sure to confirm that your peripherals are either USB 2.0 or USB 3.0. Can also use lsusb to check the list of USB devices connected, lsusb -v will print out speed (do this from a terminal on the Nano).
| Check USB 3.0 Type A | J8 |  |  | PASS | Connect mouse or keyboard, or connect a USB drive and see if it appears. Make sure to confirm that your peripherals are either USB 2.0 or USB 3.0. Can also use lsusb to check the list of USB devices connected, lsusb -v will print out speed (do this from a terminal on the Nano).
| Check Camera Modules | J2, J3 |  |  | PASS | Plug in camera module with B01 module connected, follow a tutorial to setup and use the camera. Should be plug in play
| Check Fan | J9 |  |  | PASS | Solder headers, check if PWM and Tach are working, instructions Fan spins up
| Check OLED | J13 |  |  | PASS | Solder headers, connect display, control from L4T? Simply flash fresh SD with jetbot image, OLED display should light automatically once wifi is connected
| Test Low Battery LED | D7 |  |  | PASS | Perhaps use power supply and test? Or try to drain battery somehow? Let it run with Jetbot and see if the LED turns on Test with power supply, without connecting the barrel jack
| Check Motor Control | U6 |  |  | PASS | Plug in some motors, see if you can control the motors from L4T, see what happens with the motors. Look for tutorial online. Control some GPIO and motors.
| Check NTC | J6 |  |  | PASS | If you short the pins, battery should stop charging. This mean battery temperature is too high so stop charging (NTC means decreasing resistance when increasing temperature)
| Auto power ON |  |  |  | FAIL | When power is connected, there is no jumper like on the original Jetson Nano developer kit to disable auto power on? Should still auto power on, double check RC circuitry?

## A00 Baseboard #3
Jetbot Mini A00 Baseboard Bring Up Check Items |  | Location/Ref Des | Measured | Expected | Pass or Fail | Comments
Visual and Mechanical Inspection
| Visually check all SMT components for tombstoning | - |  | -
| Visually check for solder bridges | - |  | - |  | Note that R52 is deliberately solder bridged, as otherwise the button is not connected to the rest of the circuit
| Check silkscreen | J13, J9, SW1, J14, J1, R52, D10, C59, J8, J7, J5, J6, J12, J2, J3 |  | - |  | Check R52, D10 and C59 as they were meant to be NS options and user should be able to find them easily. Other checks are connectors, I/O and other important notes. Make sure things look clean, no weird logos, make sure things are aligned and neat, no smudges. Note that D10 silkscreen is misaligned and clips into the pads of C59. C30 is marked with silkscreen for some reason? D7 silkscreen is covered by capacitor. R19 silkscreen is clipped by the resistor pads. Battery GND + is very confusing, rework (J12). D5 is marked for no reason. Barrel Jack Text is slightly clipped by U3 and C40. Need to add silkscreen for UART (J14), OLED (J13), Fan (J9).
| Check U18, F1, J5 (DC Jack), C11, C46, D5, D8, L2, L3 | U18, F1, J5, C11, C46, D5, D8, L2, L3 |  |  |  | These footprints were made by me, so make sure that all the parts look soldered on correctly C11 and C46 look a little small for the components, can't see any of the pads underneath. Double check these component?
| Module fitting in SODIMM connector | J1 |  | -
Short circuit Check
| Check for short on Barrel_Jack_Vin | J5 |  | -
| Check for short on Battery_PWR | J12 |  | -
| Check for short on Charger_Output | C19 |  | -
| Check for short on +5V_AO | U15 pin 1 |  | -
| Check for short on +5V | L3 or J14 |  | -
| Check for short on +3.3V | L1 |  | -
| Check for short on +1.8V | U24 pin 5 |  | -
| Check for short on microUSB VBUS, D+, D- nets | J7 |  | - |  | microUSB not working, so need to troubleshoot why
| Check for short on Camera Nets |  |  | -
Voltage and Current Check
| Charging Current | R38 | 1.4 A | 1.5 A |  | Use the current sense resistor R38, measure voltage across it and check V = iR for the current. Double check why the current value is off.
| Charger_Output | C19 | 12.16 V | See Comments |  | If barrel jack plugged in, should be barrel jack voltage, and if battery plugged in, should be at battery voltage, if both plugged in then should be barrel jack voltage
| 5V_AO | U15 pin 1 | 5.05 V | 4.75 - 5.25 V
| 5V | L3 | 5.20 V | 5 V |  | After pressing button turns on. Initial state is off when power is plugged in? Voltage is a little higher than expected, perhaps because of incorrect values, also double check calculations. After plugging in Jetson Nano module, more like 5.10 V?
| 3.3V | L1 | 3.248 V | 3.3 V |  | 3.3 V enable signal @3.387 V even though module is not plugged in???? Because the pin is floating, should go low once the module is plugged in, double check the pullups on all the datasheets.
| 1.8V | U24 pin 5 | 1.801 V | 1.8 V
Functional Check
| 10s button press shutdown | Short R52 and hold PWR_BTN |  |  |  | Once the module is powered on, should turn off the module.
| Button Power On | Press PWR_BTN after shutting off the module with 10s press down |  |  |  | Initial state is off when power is plugged in????? However when you press button, 5V turns on as expected
| Software Shutdown Req | After powering on the module, shutdown with software |  |  | PASS | Cannot shutdown from software, had to remove buffer as it was pulling RESET low always, which never turns on the 5V buck converter, which never powers on the module.
| UART | Power on with barrel jack, Connect FTDI friend to baseboard and host computer |  |  |  | Check if you can create a serial connection with Putty and login to the Jetson Nano. Was able to do this after making modification to 3V3 buck converter enable signal. Does 5V need to be connected? Note that PWR_LED will turn on even if just UART is connected Switch Rx and Tx on A01 to make compatible with FTDI dongle
| Force Recovery from UART (check microUSB) | Power on with barrel jack or battery, connect FTDI friend to baseboard |  |  |  | Onced powered on, use Putty to create a serial connection, stop booting and type in "enterrcm", and check for device in Windows Device manager Works at both 12 V and 19V?
| Check PWR_LED | D6 |  |  |  | Turns off and on as expected
| Get Wifi Dongle Working |  |  |  | PASS | Download drivers, establish a wifi connection, try to log in via ssh.
| Check ACOK | D3
| Check CHGOK | D4
| Check USB 2.0 Type A | J8 |  |  | PASS | Connect mouse or keyboard, or connect a USB drive and see if it appears. Make sure to confirm that your peripherals are either USB 2.0 or USB 3.0. Can also use lsusb to check the list of USB devices connected, lsusb -v will print out speed (do this from a terminal on the Nano).
| Check USB 3.0 Type A | J8 |  |  | PASS | Connect mouse or keyboard, or connect a USB drive and see if it appears. Make sure to confirm that your peripherals are either USB 2.0 or USB 3.0. Can also use lsusb to check the list of USB devices connected, lsusb -v will print out speed (do this from a terminal on the Nano). Note that testing with the Jetbot image doesn't seem to work well with mounting the drive, while working with standard Jetson Nano image works well. Note that on the Jetbot image lsusb was able to detect the device, but device could not be opened.
| Check uUSB | J7 |  |  | PASS | Enter rcm.
| Check Rpi Camera Modules | J2, J3 |  |  | PASS | Plug in camera module, follow a tutorial to setup and use the camera. Should be plug in play
| Check Fan | J9 |  |  | PASS | Solder headers, check if PWM and Tach are working, Fan spins up
| Check OLED | J13 |  |  | PASS | Solder headers, connect display, control from L4T? Simply flash fresh SD with jetbot image, OLED display should light automatically once wifi is connected
| Test Low Battery LED | D7 |  |  |  | Perhaps use power supply and test? Or try to drain battery somehow? Let it run with Jetbot and see if the LED turns on Test with power supply, without connecting the barrel jack
| Check Motor Control | U6 |  |  |  | Plug in some motors, see if you can control the motors from L4T, see what happens with the motors. Look for tutorial online. Control some GPIO and motors.
| Check NTC | J6 |  |  |  | If you short the pins, battery should stop charging. This mean battery temperature is too high so stop charging (NTC means decreasing resistance when increasing temperature)
| Auto power ON |  |  |  |  | When power is connected, there is no jumper like on the original Jetson Nano developer kit to disable auto power on? Should still auto power on, double check RC circuitry?